## Feuil1
N° | Intitulé Question | Sous intitulé | Réponse A | Réponse B | Réponse C | Réponse D | Réponse E | Réponse F | Réponse G
1 | During the Sprint Retrospective a Scrum Team has identified several high priority process improvements. Which of the following statements is most accurate? | choose the best answer | The Scrum Master selects the most important process improvement and places it in the Sprint Backlog. | The Scrum Team should choose at least one high priority process improvement to place in the Prodcut Backlog. | The Scrum Team may add the items to the Sprint Backlog for the next Sprint. | The Scrum Team should decline to add a process improvement to place in the Sprint Backlog. | The Scrum Team should decline to add aprocess improvement to the Sprint Backlog when things are running smoothy | .. | ..
2 | What is the timebox the Sprint Planning event? | choose the best answer | Monthly. | 4 hours for a one-month Sprint. | Whatever it is done. | 8 hours for a one-month Sprint. | .. | .. | ..
3 | Who is accountable for tracking the remaining work toward the Sprint Goal? | chooose the best answer | The Product Owner. | The Scrum Master. | The Developers. | The Project Manager | .. | .. | ..
4 | Several Sprints into a project, the Product Owner tells the Scrum Master that a key stakeholder just started using the product. The stakeholderis unhappy with the quality of the product. What are two good options for the Scrum Master? | choose the best two answers | Wait to bring this up until the Sprint Retrospective. | Encourage the Product Owner to put quality specifications on the Product Backlog and express the stakeholder's concern to the Developers. | Bringing the concern to the testers to improve how the Product is verified. | Explain to the Product Owner that it is up to the Developers to decide on acceptable quality standards. | Coach the Product Owner on how to talk with Developers about this concern. | .. | ..
5 | What is the accountability of the Product Owner during Sprint 0? | choose the best answer | There is no such thing as Sprint 0. | Make sure enough Product Backlog items are refined to fill the first 3 Sprints. | Determine the composition of the Scrum Team to meet the release plan. | Gathering, eliciting, and analyzing the requirements to build the Product Backlog. | .. | .. | ..
6 | Which of the following might the Scrum Team discuss during a Sprint Retrospective? | choose the best answer | Methods of communication | The way the Scrum Team does Sprint planning | Skills needed to improve the Developers ability to deliver . | The Definition of Done | All of the above | .. | ..
7 | Who determines how work is performed during the Sprint? | choose the best answer | Team manager | Subject Master | The Developers | The Scrum Team should decline to add a process improvement to place in the Sprint Backlog. | .. | .. | ..
8 | If burndown charts are used to visualize progress, what do they track? | choose the best answer | Accumulated cost. | Individual worker productivity. | Accumulated business value delivered to the customer. | .. | .. | .. | ..
9 | When is a Product Backlog item considered complete? | choose the best answer | When the item has gain. | When the item passes all acceptance criteria. | When the item meets the Definitin of Done. | At the end of the Sprint. | .. | .. | ..
10 | Which three of the following timeboxed events in Scrum? | choose the best three answers | Sprint 0 | Sprint Retrospective | Sprint Planning | Sprint Testing. | Daily Scrum | Release Retrospective | Release Planning
11 | The Developers select a set of Product Backlog items for a Sprint Backlog withthe intent to get the selected items done by theend of the Sprint. Which three phrases best describe the purpose of a Definition of Done | choose the best three answers | It defines what it takes for an Increment to be ready for release. | It guides the Developers in creating a forecast at the Sprint Planning. | It controls whether the developers have performed their tasks. | It tracks the percentage completeof a Product Backlog item. | It provides a template for elements that need tobe includedin the documentation. | It creates transparency over the work inspected at the Sprint Review. | ..
12 | What is the Product Owner responsible for during the Sprint Retrospective? | choose the best answer | Summarizing and reporting the discussions to the stakholdersthat they represent in the Scrum Team | Participating as a Scrum Team member. | Capturing requirements for the Product Backlog. | The Product Owner should not take part in Sprint Retrospective. | .. | .. | ..
13 | During a Sprint Retrospective , the Developers propose moving the Daily Scrum to only occur on Tuesday and Thursday. Which two are the most appropriate responses for the Scrum Master to recommend? | choose the best two answers | Acknowledge and support the self-managing team's decision. | Consider the request and decide on which days the Daily Scrum should occur. | Coach the team on why the Daily Scrum is important as an opportunity to update plan. | Learn why the Developers want this and work with them to improve the outcome of the Daily Scrum. | .. | .. | ..
14 | When is it most appropriate for a Scrum Team to change the Definition of Done? | choose the best answer | Prior to starting a new spirit | During the Sprint Retrospective . | During Spring Planning. | Prior to starting a new project. | .. | .. | ..
15 | The Daily Scrum is an event that happens every day.What would be three key concerns if the frequency were to be lowered to every two or three days? | choose the best three answers | The Sprint Backlog may become inaccurate? | Impediments are raised and resolved more slowly. | Opportunities to inspect and adapt the Sprint Backlog are lost. | Too much work is spent updatingthe Scrum board before the meeting. | The Product Owner cannot accurately report progress to the stakeholders. | The Scrum Master loses the ability to update the Gantt chart properly. | ..
16 | Who is accountable for clearly expressing Product Backlog items? | choose the best answer | The business analyst who represents the Product Owner . | The Scrum Master. | The Scrum Master, or the Scrum Master may have the Developers do it. | The Product Owner. | .. | .. | ..
17 | What is the timebox for the Sprint Review? | choose the best answer | 2 hours for a one-month Sprint. | 1 day. | 4 hours for a one-month Sprint. | As long as needed. | .. | .. | ..
18 | The timebox for a Daily Scrum is ? | choose the best answer | Two minutes per person. | 15 minutes. | 4 hours. | The same time of days every day. | .. | .. | ..
19 | Which two ways of creating Scrum Teams are consistent with Scrum's values? | choose the best two answers | Brig all the peoople together and let them organize into Scrum Teams. | Managers personally re-assign current subordinates to new teams. | Existing teams propose how they would like to go about organizing into the new structure. | The Chief Product Owner determines the new team structures and assignments. | Managers collaborate to assign individuals to specific teams. | .. | ..
20 | Which outcome is expected as Scrum Team matures? | choose the best answer | They will improve their Definition of Done to include more stringent criteria. | A Scrum Master is no longer needed since they are a mature team now. | The Sprint Retrospectives will grow to be longer than 4 hours. | Sprint Reviews will no longer be needed. | There will be no need for a timeboxed Sprint. | .. | ..
21 | When multiple teams work together on the same product , each team should maintain a separate Product Backlog. | True or false | True | False | .. | .. | .. | .. | ..
22 | What are two effective ways for a Scrum Team to ensure security concerns are satisfied? | choose the best two answers | Delegate the work to the security department. | Postpone the work until a specialist can perform a security about audit and create a list of security-related Product Backlog items. | Add security concerns to the Definition of Done . | Add a Sprint to specifically resolve all security concerns. | Have the Scrum Team create Product Backlog items for each concern. | .. | ..
23 | Choose two responsibilities of self-managing Developers. | choose the best two answers | Pull Product Backlog items for the Sprint. | Increase daily progress to stakeholders. | Do the work plannned in the Sprint Backlog. | Reorder the Product Backlog. | .. | .. | ..
24 | Why does the Product Owner want the Developers to adhere to its Definition of Done? | choose the best answer | To know what the team will deliver over the next three Sprints. | To predict the team's productivity over time. | To be able to reprimand the team when they do not meet their velocity goal for the Sprint. | To have complete transparency into what has been done at the end of each Sprint. | .. | .. | ..
25 | When multiple Scrum Teams are working on the same product, should all of their Increments be integrated every Sprint? | choose the best answer | Yes, in order to accurately inspect what is done. | No, each Scrum Team stands alone. | Yes, but only for Scrum Teams whose work has dependencies. | No, that is far too hard and must be done in a hardering Sprint. | .. | .. | ..
26 | The Sprint Review is mainly an inspect and adapt opprtunityfor which group? | choose the best answer | The Scrum Team and stakeholders. | The Product Owner and the Developers. | The Product Owner and management. | The Developers and stakeholders. | The Developers and mmanagement. | The Product Owner and stakeholders. | ..
27 | You have just been hired by a company new to Scrum. Your management has assigned you to be the Scrum Master of sx new Scrum Teams. These teams will build one product. Select two conditions you should strive for this scenario. | choose the best two answers | There should be six Product Owners, one for each Scrum Team. | There should be only one Product Owner. | Each Scrum Team should have a separate Product Backlog. | The product has one Product Backlog. | There should be six product Owners, reporting to a Chief Product Owner. | .. | ..
28 | What does it mean for a Scrum Team to be cross-functional? | choose the best answer | Developers on the Scrum Team work closely with business analysts, architects,developers, and testers who are not on the team. | The Scrum Team includes cross-skilled individuals who are able to contribute to do what is necesssary to deliver an Increment. | The Scrum Team is a virtual team drawing from sepparate teams of business, analysts, architecs, developers, and testers. | The Scrum Team includes not only developers but also business analysts, architects, and testers. | .. | .. | ..
29 | What may be included in the Sprint Backlog? | chooose the best answer | User stories | Tasks. | Use cases. | Tests. | Any of the above ( or others) which are a decomposition of the selected Product Backlog items. | .. | ..
30 | Cross-functional teams are optimized to work on one component or layer of a system only. | True or false | True | False | .. | .. | .. | .. | ..
31 | A Developer takes the Scrum Master aside to express his concerns about data security issues. What should the Scrum Master do? | choose the best answer | Ask the Developer to share the concern with the team as soon as possibel. | Tell the Product Owner to stop further development of features until the issues are fixed. | Go check with the testers. | Add security to the Definition of Done. | Create a Product Backlog itm for security. | .. | ..
32 | Which of the following are true about the length of the Sprint? | choose the best answer | Sprint length is determined during Sprint Planning, and should hold the time it will take to code the planned features in the upcoming Sprint, but does not include time for any testing. | The length of the Sprint should be proportional to the work thatis done in between Sprints. | All Sprint must be one month or less. | Sprint length is determined during Sprint Planning, and should be long enough to make sure the Scrum Team can deliver what is to be accomplished in the upcoming Sprint. | .. | .. | ..
33 | A Scrum Team is required to deliver a done Increment by the end of a Sprint. S elect two statements that expalin what done means. | choose the best two answers | Ready to be released to end users. | No work is left to meet the Definition of Done. | Ready for integration. | All work the Developers are willing to do. | Whatever the Product Owner defines as quality. | .. | ..
34 | What are three ways Scrum promotes self-management? | choose the best three answers | By removing titles for Scrum Team members. | By being a lightweight framework. | By having the Scrum Master protect the Scrum Team from interruptions. | By the Scrum Team deciding what work to do in a Sprint. | .. | .. | ..
35 | Who should know the most about the progress toward the Product Goal? | choose the best answer | The Project Manager. | The Developers | The Scrum Master. | The Product Owner. | .. | .. | ..
36 | Developers do not meet with stakeholders; only the Product Owner meets with stakeholders | True or false | True | False | .. | .. | .. | .. | ..
37 | In accordance with Scrum theory, how should a group of 100 people be divided into multiple Scrum Teams? | choose the best answer | Understanding the product, the product vision and the rules of the Scrum framework, the people divide themselves into teams. | Check with the allocation department to see who has worked together before and make these first teams. | It does not really matter since you can rotate the teams every Sprint to spread knowledge. | Create a matrix of skills, seniority, and level of experience to assign people to teams. | .. | .. | ..
38 | What is the role of management in Scrum? | choose the best answer | To continually monitor staffing levels of the Scrum Team. | To identify and remove people that are not working hard enough. | To monitor the productivity of the Developers. | To present the Scrum Teams with insights and resources that help them improve. | .. | .. | ..