## Feuil1
N° | Intitulé Question | Sous intitulé | Réponse A | Réponse B | Réponse C | Réponse D | Réponse E | Réponse F | Réponse G
1 | How do you know that a Scrum Team is cross- functional? | chooose the best answer | There are no conflicts within the Scrum Team. | A few of the Developers pair program and do Test Driven Development. | The Scrum Team has all the skills to createand Increment by end of every Sprint. | Every memeber of the Scrum Team is able to perform every task. | .. | .. | ..
2 | When many Scrum Teams are working on a single product, what best describes th e definition of Done? | choose the best answer | The Scrum Masters from each Team define a common Definition of Done. | All Scrum Teams must have a definition of Done that makes their combined work potentially releasable. | Each Scrum Team uses its own, but must make their definition clear to all otherteams so the differences are known. | Each Scrum Team defines and uses its own. The differences are discusssed and reconciled during a hardening Sprint. | .. | .. | ..
3 | What techniques could the Scrum Master use when the Scrum Team gets caught in an internal disagreement about which agile practices to apply? | choose the best two answers | Involve the complete Scrum Team in making a decision | Ask team members to take the issue up with the company's Humain Resources departement. | Use coaching techniques, such as open questions and active listening. | .. | .. | .. | ..
4 | Developers are self-managing, which of the following do they manage? | choose the best answer | Stakeholders for the Sprint Review . | Sprint Backlog. | Product Backlog ordering. | When to release, based on its progress. | Sprint lenght. | .. | ..
5 | A Scrum Team is cohesive unit of professionals that consists of the following? | choose all that apply | Users. | One Scrum Master. | Developers. | Customers. | One Product Owner. | .. | ..
6 | During Sprint Planning the Product Owner and the Developers are unable to reach an understanding about the highest order Product Backlog items. Because of this, the Developers are unable to determine how many Product Backlog items they can forecast for the upcoming Sprint. However , the Prodct Owner and the Developers are able to agree on a Sprint Goal . Which of the following actions should the Scrum Master support? | choose the best two answers | Cancel the Sprint. Send the entire team to an advanced Scrum training and then start a new Sprint. | During the next Sprint Retrospective discuss why this happened and what changes will make it less likely to recur. | Forecast the Product Backlog items that are most likely to meet the Spirit Goal and create the Spirit Backlog. Conclude Sprint Planning and start the development work. Continue to analyse, decompose,and create additional functionality during the Spirit. |  |  | .. | ..
7 | The Scrum Team should have all skills needed to: | choose the best answer | Complete the project within the date and cost as calculated by the Product Owner. | Do all of the development work, except for specialized testing that requires additional tools and enironments. | Turn Product Backlog items inot a valuable, useful Increment. | .. | .. | .. | ..
8 | What is the main reason for a Scrum Master to be at the Daily Scrum? | choose the best answer | To make sure every team memeber answers the three questions. | To gather status and progress information to report to management. | He or she does not have to be there; he or she only has to ensure the Developers have a Daily Scrum. | To write down any changes to the Sprint Backlog, including adding new items, and tracking progress on the burn-down. | .. | .. | ..
9 | How much time is required after a Sprint to prepare for the next Sprint? | choose the best answer | The break between Sprints is timeboxed to one-week for a one-month Sprint, and usually less for shorter Sprints. | Enough time for the requirements for the next Sprint to be determined and documented. | Enough time for the Developers to finish the testing from last Sprint. | None. A new Sprint starts immediately following the end of the previous Sprint. | All of the above are allowed depending on the situation. | .. | ..
10 | What if the Scrum Team cannot complete its work by the end of the Sprint? | choose the best answer | The Sprint length is unchanged and the Scrum Team continuously learns and adapts. | The Sprint is extended temporarily. Lessons are taken to ensure it does not happen again. | The Sprint is extended and future Sprints use this new duration. | .. | .. | .. | ..
11 | The purpose of a Sprint is to produce a valuable and useful increment . | True or false | True | False | .. | .. | .. | .. | ..
12 | Who must attend the Daily Scrum? | choose the best answer | The Developers and Scrum Master. | The Developers and Product Owner. | The Developers | The Scrum Team. | The Scrum Master and Product Owner. | .. | ..
13 | Which of the following is a Developer accountable for ? | choose the best two answers | Creating a plan for the Sprint, the Sprint Backlog. | Organizing the work required to meet the Sprint Goal. | Reporting productivity. | Selecting the Product Owner. | .. | .. | ..
14 | If two Scrum Teams are added to the development of a product that previously had only one Scrum Team, what will be the immediate impact on the prodcutivity of the original Scrum Team? | choose the best answer | Its productivity is likely to increase. | Its productivity is likely to decrease. | Its productivity is likely to stay the same. | We do not know until a Sprint has run. | .. | .. | ..
15 | Who is responsible for engaging stakeholders? | choose the best answer | The Developers. | The Scrum Team. | The Business Analyst. | The Project Manager | The Team Manager. | .. | ..
16 | Who determines when it is appropriate to update the Sprint Backlog during a Sprint? | choose the best answer | The Product Owner | The Project Manager. | The Developers. | The Scrum Team. | .. | .. | ..
17 | For which ofthe following is the Scrum Master responsible? | choose the best answer | Properly adopting and using the Scrum framework. | Keeping track of resource allocation. | Managing the performance of the Scrum Team. | The meetings and the objectives that a Scrum Team sets for itself. | .. | .. | ..
18 | During a Sprint, when is new work or further decomposition of work added to the Sprint Backlog? | choose the best answer | As soon as possible after it is identified. | When the Scrum Master has time to enter it. | During the Daily Scrum after the Developers approve it. | When the Product Owner identifies new work. | .. | .. | ..
19 | Multiple Scrum Team working on the same product or systemall select work from the same Product Backlog. | True or false | True | False | .. | .. | .. | .. | ..
20 | A high-perfoming Scrum Team will have at least one Release Sprint. | True or false | True | False | .. | .. | .. | .. | ..
21 | What is the recommended size for a Scrum Team? | choose the best answer | 9 | 7 plus or minus 3. | 10 or fewer. | At least 7. | .. | .. | ..
22 | Which of these may a Scrum Team deliver at the end of a Sprint? | choose the best answer | A single document, if that is what managementasked for. | Failing unit tests, to identify acceptance tests for the next Sprint. | A valuable, useful Increment that meets the Definition of Done. | An Increment of software with minor know bugs. | .. | .. | ..
23 | As the Sprint Planning progresses, the Developers realize that the workload may be greater than their capacity to complete the work.Which two are valid actions? | choose the best two answers | Cancel the Sprint. | The Developers work overtime during this Sprintt; | Recruit additional Developers before the work caan begin. | The Developers ensure that the Scrum Team is aware, start the Sprint , and monitor progress. | Remove or change selected Product Backlog items. | .. | ..
24 | When must a Product Owner release each Increment? | chooose the best answer | When it makes sense. | After every Sprint, without exception. | Whenever the product is free of delects. | When the Scrum Team finishes their work. | .. | .. | ..
25 | A Scrum Team is experiencing a growing list of impediments. Which techniques would be most helpful in this situation? | choose the best two answers | The Scrum Master discusses the impediments with the Scrum Team. | The Product Owner should add the open impediments to the Product Backlog. | Arrange a triage meeting with management. | As aScrum Team, prioritize the list and work on themin order. | .. | .. | ..
26 | Which statement best describes the Sprint Review | choose the best answer | It is a mechanism to control the Developers activities during a Sprint. | It is used to congratulate the Developers if they complete their forecast or to punish the Developers if they fail to meet their forecast. | It is when the Scrim Team and stakeholders inspect the outcome of a Sprint and figure out what to do next. | It is a demo at the end of the Sprint for everyone in the organization to check on the work done. | .. | .. | ..
27 | The Product Owner makes sure the Developers select enough from the Product Backlog for a Sprint to satisfy the stakeholders. | True or false | True | False | .. | .. | .. | .. | ..
28 | How should a Scrum Team deal with non-functional requirements? | choose the best answer | Manage them during the integration Sprint prior to the Release Sprint. | Assign them to the lead developerson the team. | Ensure every Increment meets them. | Make sure the release department understands these requirements , but it is not the Scrum Team's responsibility. | .. | .. | ..
29 | You are the Scrum Master on a newly formed Scrum Team. Which two of the following activities would probably help the team in starting up? | choose the best two answers | Have the manager for each Developer introduce their direct reports and go over their reponsibilities on the Scrum Team. | Ensure the team understands they need a Definition of Done. | Introduce a bonus system for the top performers in the team. | Ensure the Scrum Team members have compatible personalities. | Ask the Product Owner to discuss the product , its vision, history, goals,and context, as well answer questions. | .. | ..
30 | How often Scrum Team membership change? | choose the best answer | As needed, while taking into account a short-term reduction in productivity . | Every Sprint to promote shared learning. | As needed,with no special allowance for changes in productivity. | Never, it reduces productivity. | .. | .. | ..
31 | How should Product Backlog items be chosen when multiple Scrum Teams work from the same Product Backlog? | choose the best answer | The Developers pull in work in agreement with the Product Owner. | The Product Owner should provide each team with its own Product Backlog. | The Product Owner decides. | The Scrum Team with the highest velocity pulls Product Backlogitems first. | Each Scrum Team takes an equal number of items. | .. | ..
32 | What tactic should a Scrum Master use to divide a group of 100 people inot multiple Scrum teams? | choose the best answer | Ask the people to divide themselves into teams. | Create teams based on their skills across multiple layers ( such as database, UI,etc.) | Ask the Product Owner to assign the people yo teams. | .. | .. | .. | ..
33 | Which are appropriate topics for discussion in a Sprint Retrospective? | choose the best three answers | Definition of Done. | How the Scrum Team does its work. | Team relations. | The value of work currently represented in the Product Backlog. | Arranging the Sprint Backlog for the next Sprint . | .. | ..
34 | A Scrum Master fulfills the same role as traditonal Project Manager. | True or false | True | False | .. | .. | .. | .. | ..
35 | Every Scrum Team must have a Product Owner and Scruum Master | True or false | False: A Scrum Master is only required when asked for by the ScrumTeam. | True: Each must be 100% dedicated to the ScrumTeam. | False: A Product Owner can be replaced by a subject matter expert in the Scrum Team. | True: Outcomes are affected by their participation and availibility. | .. | .. | ..
36 | What is the recommended size for a Scrum Team? | choose the best answer | Typically 10 or fewer people. | Minimum of 7. | 7 or lus or minus 2. | 9 | .. | .. | ..
37 | What are two responsabilities of testers in a Scrum Team? | choose the best two answers | Tracking quality metrics. | Scrum has no "tester" role. | Verifying the work of programmers. | The Developers are responsible for quality. | Finding bugs. | .. | ..